## Sheet1
Question type 0 = Single answer 1 =Multiple answer 2=Match the column 3=Short answer 4=Long answer | Question | Description | correct option number | Option 1 | Option 2 | Option 3 | Option 4
0 | What are the Five Project Management Process Groups in order? |  | 4 | Initiating, Planning, Monitoring & Controlling, Executing, and Closing. | Initiating, Monitoring & controlling, Planning, Executing, and Closing | Initiating, Executing, Planning, Monitoring & Controlling, and Closing | Initiating, Planning, Executing, Monitoring & Controlling. and Closing
0 | Which statement relates to the definition of the Planning Process? |  | 3 | Defines and Authorises Project or Phase | Coordinate resources to carry out the plan | Defines and refines the project objectives | Ensuring that project objectives are
0 | You are a Project Manager in a Highway Construction Project. You are now working if there are changes to the scope, schedule, budget of the project. These assignments are part of which process. |  | 4 | Initiating | Planning | Executing | Monitoring and Controlling
0 | Integration Management deals with: |  | 4 | Making sure that every body knows what he should know to accomplish the project | Ensuring that you as a project manager have every detail of the product which will be produced | Integrates project managers, sponsors, and senior management | Deals how to coordinate all the work and how to deal with changes
0 | Project management is: |  | 4 | The centralized coordinated management of a program to achieve the program's strategic objectives and benefits. | The application of information systems to manage in a coordinated way a group of related projects. | The centralized coordination of operations and programs to achieve the program's strategic objectives and benefits. | The application of knowledge, skills, tools and techniques to project activities to meet the project requirements.
0 | The nine knowledge areas are: |  | 2 | Scope, initiation, price, risk, communication, IT, procurement, schedule, and quality | Procurement, integration, scope, cost, quality, time, risk, HR, and communication | Integration, listerine, time, cost, quality, procurement, risk, HR, communication | Integration, scope, schedule, budget, quality, IT, training, communication
0 | A stakeholder analysis: |  | 4 | Produces an understanding of how the project is structured and if there is further milestones needed. | Determines whether stakeholders feel the project is an acceptable and cost-effective approach to address the business need. | Determines the grant of authority or rights, stating that the granter formally recognizes the prerogative of the recipient to exercise the rights specified. | Produces an understanding of how best to manage individuals who have a vested interest in the outcome of the project.
0 | A project management plan is: |  | 1 | A formal, approved document that defines how the project will be executed, monitored and controlled. | The aggregation of the tools and techniques needed to manage a project. | Contains only the plans for each of the triple constraints and their baselines. | A document that graphically depicts the project team members and their interrelationships for a specific inter relational diagram to discover root causes.
0 | When creating a WBS, you should use which method: |  | 3 | Top-down | Bottom-up | Either A or B | None of the above-you shouldn't be creating a WBS, just use MS Project.
0 | The activities you should do to manage project risk are: |  | 1 | Plan your risk plan, then identify, quantify, analyze, develop plans, monitor and control. | Throw a bunch of money in a risk slush fund and use it as needed, then if it isn't used, you can throw a fantastic party! | Some projects don't have risks, so only make plans when absolutely necessary. | Monitor risks and when applicable mitigate, transfer, avoid, or accept risks.
0 | Earned value is: |  | 1 | The value of work performed expressed in terms of the approved budget assigned to that work for a schedule activity. | The authorized budget assigned to the scheduled work to be accomplished for a schedule activity. | The value of work performed to get the maximum benefit with the minimum effort. | The amount of good will deposited in a stakeholders emotional bank account.
0 | One of the following groups is NOT a process group - but which one? |  | 2 | Planning | Integrating | Closing | Executing
0 | Your project team has been assembled, so in which process group will you perform team building? |  | 1 | Executing | Initiating | Planning | Monitoring and Controlling
0 | When estimating time for activities, a Project Manager should: |  | 2 | Use the best guess and estimate all activities since there will be changes as the project progresses and more information becomes available | Involve people who will be doing the work to get estimates | Estimate for what the cost will allow and include buffers | None of the above
0 | Estimating a task duration by extrapolating from one or more similar activities completed in the past is called |  | 4 | Parametric estimating. | Estimating by extension. | History based estimating. | Analogous estimating.
0 | Cost of changes in requirements tends to: |  | 1 | Increase as the project starts up and progresses | Decrease as the project starts up and progresses | Increase or decrease depending on the scope of the change | Always require the project sponsor's approval
0 | As the project manager, you are scheduling some activities in which there is a delay between the finish of the activity and the start of the successor activity. These dependencies would be reflected in the schedule with a |  | 2 | Finish-to-start relationship | Lag | Start-to-finish relationship | Lead
0 | The authority to approve or deny change request lies with |  | 4 | Project Manager | Customer | Project Sponsor | Change Control Board
0 | Which of the following is true statement about risks? |  | 4 | If a risk is identified in a risk response plan, then that means that risk has already happened. | Once a risk has happened, you refer to the risk management plan to determine what action needs to be taken. | A risk that was not planned but has happened is called a trigger. | Risk identification happens in all the phases of the project.
0 | You join a projectized organization as a project manager. Which of the following best describes your level of authority? |  | 3 | Low to moderate | Moderate to high | High to almost total | Little or none