## Sheet1
Question type 0 = Single answer 1 =Multiple answer 2=Match the column 3=Short answer 4=Long answer | Question | Description | correct option number | Option 1 | Option 2 | Option 3 | Option 4
0 | One of the most important characteristics of an effective project manager is to be able to: |  | 1 | Communicate clearly and effectively with all stakeholders. | Be able to understand and do all of the technical work required to complete the project. | Create quality quality plans. | Lead dynamic presentations to the customer.
0 | A project management plan is: |  | 1 | A formal, approved document that defines how the project will be executed, monitored and controlled. | The aggregation of the tools and techniques needed to manage a project. | Contains only the plans for each of the triple constraints and their baselines. | A document that graphically depicts the project team members and their interrelationships for a specific inter relational diagram to discover root causes.
0 | A project plan is: |  | 3 | A formal, approved document that defines how the project will be executed, monitored and controlled. | The aggregation of the tools and techniques needed to manage a project. | The plans for each of the triple constraints and their baselines. | A document that graphically depicts the project team members and their interrelationships for a specific inter relational diagram to discover root causes.
0 | The most often neglected and forgotten process group is: |  | 3 | Integration | Initiation | Close out | HR
0 | When creating a WBS, you should use which method: |  | 3 | Top-down | Bottom-up | Either A or B | None of the above-you shouldn't be creating a WBS, just use MS Project.
0 | The most common type of activity relationship is (also the default on MS Project): |  | 4 | Start-to-Finish | Finish-to-Finish | Start-to-Start | Finish-to Start
0 | Relationships that are inherent in the nature of work being done and often involve physical limitations are called: |  | 1 | Mandatory dependencies | Soft dependencies | Discretionary dependencies | External dependencies
0 | The activities you should do to manage project risk are: |  | 1 | Plan your risk plan, then identify, quantify, analyze, develop plans, monitor and control. | Throw a bunch of money in a risk slush fund and use it as needed, then if it isn't used, you can throw a fantastic party! | Some projects don't have risks, so only make plans when absolutely necessary. | Monitor risks and when applicable mitigate, transfer, avoid, or accept risks.
0 | To create excitement, on-board team members and set the expectations of the project, as a project manager you should hold a: |  | 4 | Tollgate review | A rave | Stakeholder drive | Kickoff party
0 | The cure for scope creep is: |  | 1 | To clearly identify what work will be completed and what work will not be included and then follow a scope change request process. | To clearly document the scope of work to be done and then follow the integration change process. | Use scope frequently and invest in Proctor and Gamble. | To be sure to communicate with the customer the scope of the project and follow the project plans.
0 | Earned value is: |  | 1 | The value of work performed expressed in terms of the approved budget assigned to that work for a schedule activity. | The authorized budget assigned to the scheduled work to be accomplished for a schedule activity. | The value of work performed to get the maximum benefit with the minimum effort. | The amount of good will deposited in a stakeholders emotional bank account.
0 | Which focuses on the centralized management to achieve specific strategic business objectives by identifying, prioritizing, authorizing, managing, and controlling projects, programs, and other related work? |  | 3 | Program management | Project management | Portofolio management | Division management
0 | Which process uses up most of the budget in a project? |  | 3 | Integrating | Planning | Executing | Monitoring and Controlling
0 | One of the following groups is NOT a process group - but which one? |  | 2 | Planning | Integrating | Closing | Executing
0 | Work in the future distance is planned at a high level on the work breakdown structure (WBS), but work in the near future can be planned in detail at a low level on the WBS. What is this form of progressive elaboration called? |  | 4 | Stage Gate Planning | Detailed Phase Planning | Progressive Planning | Rolling Wave Planning
0 | The project life cycle is documented in which process group? |  | 1 | Planning | Initiating | Integration | Life Cycle Planning
0 | Your project team has been assembled, so in which process group will you perform team building? |  | 1 | Executing | Initiating | Planning | Monitoring and Controlling
0 | What is meant by RACI? |  | 4 | Responsible, Accountable, Confirm, Inform | Recommended, Accountable, Consulted, Inform | Responsible, Accountant, Consulted, Inform | Responsible, Accountable, Consulted, Inform
0 | The project manager meets with the project team to review lessons learned from previous projects. In what activity is the team involved? |  | 3 | Performance management | Scope identification | Risk identification | Project team status meeting
0 | When estimating time for activities, a Project Manager should: |  | 2 | Use the best guess and estimate all activities since there will be changes as the project progresses and more information becomes available | Involve people who will be doing the work to get estimates | Estimate for what the cost will allow and include buffers | None of the above