## Sheet1
Question type 0 = Single answer 1 =Multiple answer 2=Match the column 3=Short answer 4=Long answer | Question | Description | correct option number | Option 1 | Option 2 | Option 3 | Option 4
0 | Key features of a project management office (PMO) generally include all of the following EXCEPT: |  | 1 | Delivering specific project objectives and controlling the assigned project resources to best meet objectives of the project. | Identification and development of project management methodology, best practices, and standards. | Centralized repository and management for both shared and unique risks for all projects. | A mentoring platform for project managers.
0 | Your project budget is USD 400,000. Most of this money will be spent during: |  | 2 | Project plan development. | Project plan execution. | Project control. | Project initiation.
0 | Estimating a task duration by extrapolating from one or more similar activities completed in the past is called |  | 4 | Parametric estimating. | Estimating by extension. | History based estimating. | Analogous estimating.
0 | A change control board is |  | 2 | A formally constituted group of stakeholders responsible for minimizing the number of approved changes, with all decisions and recommendations being recorded.. | A formally constituted group of stakeholders responsible for reviewing, evaluating, approving, delaying or rejecting changes to the project, with all decisions and recommendations being recorded. | Functionally equivalent to a project steering committee. | Any group of stakeholders that meets to review or approve changes
0 | The sequence of activities that cannot be delayed during the course of the project is referred to as the: |  | 1 | Critical path | Master schedule | Slack line | Action plan
0 | Cost of changes in requirements tends to: |  | 1 | Increase as the project starts up and progresses | Decrease as the project starts up and progresses | Increase or decrease depending on the scope of the change | Always require the project sponsor's approval
0 | The critical path in a schedule network is the path that: |  | 1 | Takes the longest time to complete | Must be done before any other tasks | Allows some flexibility in scheduling a start time | Is not affected by schedule slippage
0 | All of the following are common characteristics of project life cycle descriptions EXCEPT : |  | 2 | Cost and staffing levels are low at the start, higher towards the end and drop rapidly as the project ends | Risk and uncertainty are highest at the end of the project | The probability of successfully completing the project is low at the start and gets progressively higher as the project continues | The ability of stakeholders to influence the final characteristics of the project product is highest at the start of the project
0 | As the project manager, you are scheduling some activities in which there is a delay between the finish of the activity and the start of the successor activity. These dependencies would be reflected in the schedule with a |  | 2 | Finish-to-start relationship | Lag | Start-to-finish relationship | Lead
0 | Which of these is not an example of a project? |  | 4 | Buying clothes from the market on a special sale. | Planning for your friends wedding. | Building a bridge across the Amazon river. | Cleaning the office building every day.
0 | You are planning to use PERT for planning of your project. A task has pessimistic estimate of 24 days, most likely estimate of 15 days and optimistic estimate of 12 days. What is the mean using the PERT technique? |  | 4 | 18 days | 25.5 days | 15 days | 16 days
0 | The authority to approve or deny change request lies with |  | 4 | Project Manager | Customer | Project Sponsor | Change Control Board
0 | You are required to estimate the time to paint a large wall. You know it takes two hours to paint one square foot of wall. The wall has an area of 30 square foot. So you estimate that it will take 60 hours to paint the wall. Which estimation model are you using? |  | 2 | Bottom-up | Parametric | Analogous | Expert judgment
0 | You are the project manager responsible for building a new web site. The project is running late. To bring the project on schedule, you decide to add additional resources to the critical path. This is an example of |  | 3 | Fast-tracking | Resource planning | Crashing | Schedule Management
0 | Which of the following is true statement about risks? |  | 4 | If a risk is identified in a risk response plan, then that means that risk has already happened. | Once a risk has happened, you refer to the risk management plan to determine what action needs to be taken. | A risk that was not planned but has happened is called a trigger. | Risk identification happens in all the phases of the project.
0 | The PMBOK® Guide is the standard for: |  | 3 | Managing all projects all of the time. | Managing all projects most of the time. | Managing most projects most of the time. | Managing some projects some of the time.
0 | The five Project Management Process Groups are: |  | 2 | Planning, Checking, Directing, Monitoring, and Recording. | Initiating, Planning, Executing, Monitoring and Controlling, and Closing. | Planning, Executing, Directing, Closing, and Commissioning. | Initiating, Executing, Monitoring, Evaluating, and Closing
0 | You join a projectized organization as a project manager. Which of the following best describes your level of authority? |  | 3 | Low to moderate | Moderate to high | High to almost total | Little or none
0 | Your team is in the middle of executing a project that is now projected to run three weeks too long. Which of the following adjustments would allow the project to be delivered on time? |  | 2 | Substitute a lesser experienced programmer for a more experienced one | Move resources from a non-critical task to a critical path task | Modify the purchase of new equipment to less expensive equipment | Allow a tester on the project to temporarily work on another, more critical project
0 | During which phase of the project would you suggest using an integrated change control process? |  | 1 | Throughout the project | Initiation | Closure | Execution